## NV Infill B&S
Residential multi-dwelling pre constructoin workflow
Preliminary planning
Responsible | Team | Task | Triggering task | days | NOTE
Management |  | Project team pre-planning meeting completed | Outer boundary & detailed survey Ordered ¦ Project program completed ¦ Book council meeting to discuss proposed plan ¦ Project Marketing strategy ordered ¦ Demolition Required | 0¦0¦0¦0¦0
|  | Project program completed | New electricity meter service connected ¦ New gas meter service connected | 0¦0
|  | Outer boundary & detailed survey Ordered | Outer boundary & detailed survey complete ¦ Book council meeting to discuss proposed plan ¦ Project Marketing strategy ordered | 21¦0¦0
Outer boundary & detailed survey complete
|  | Book council meeting to discuss proposed plan | Council meeting complete | 7¦
|  | Council meeting complete | Final concept plans ordered | 0¦
|  | Project Marketing strategy ordered | Project Marketing Strategy complete | 1¦
Project Marketing Strategy complete
|  | Demolition Required | Demolition quote requested | 0¦
|  | Final concept plans ordered | Final concept plans completed | 3¦
|  | Final concept plans completed | Planning drawings ordered | 0¦
|  | New electricity meter service connected | Elec abolishment ordered | 14¦
|  | New gas meter service connected | Gas abolishment ordered | 14¦
|  | Elec abolishment ordered | Elec services abolishment approved | 5¦
|  | Gas abolishment ordered | Gas services abolishment approved | 5¦
|  | Gas services abolishment approved | Gas abolished confirmed | 5¦
|  | Elec services abolishment approved | Confirm SAPN electricity abolishment request sent to SAPN by service provider | 0¦
|  | Confirm SAPN electricity abolishment request sent to SAPN by electricity provider | Electricity abolishment booked with SAPN | 5¦
|  | Electricity abolishment booked with SAPN | Electricity abolished | 14¦
|  | Electricity abolished | Electricity abolishment site check | 2¦
Electricity abolishment site check
|  | Gas abolished confirmed | Gas abolished site check | 2¦
Gas abolished site check
|  | Planning drawings ordered | Planning drawings complete ¦ EPA report ordered ¦ Native veg report ordered ¦ Arborist report ordered ¦ Site & Drainage stormwater plan ordered ¦ Land division plans ordered ¦ Hydraulics services ordered (Sewer, water, gas) ¦ Telecomunications ordered (NBN, Telstra ¦ Electrical services ordered ¦ Preliminary footing construction report ordered ¦ Preliminary civil road design ordered ¦ Soil/ Geotech ordered ¦ Wastewater septic Report ordered ¦ Landscaping concept plan ordered | 3¦0¦0¦0¦0¦0¦0¦0¦0¦0¦0¦0¦0¦0
Planning drawings complete
|  | Landscaping concept plan ordered | Landscaping concept plan complete | 14¦
Landscaping concept plan complete
|  | EPA report ordered | EPA report complete | 21¦
EPA report complete
|  | Native veg report ordered | Native veg report complete | 28¦
Native veg report complete
|  | Arborist report ordered | Arborist report complete | 21¦
Arborist report complete
Hydraulics services ordered (Sewer, water, gas)
Telecommunications ordered (NBN, Telstra)
Electrical services ordered
|  | Site & Drainage stormwater plan ordered | Site & Drainage stormwater plan Complete | 14¦
Site & Drainage stormwater plan Complete
|  | Preliminary civil road design ordered | Preliminary civil road design completed | 5¦
|  | Preliminary civil road design completed | Preliminary civil design saved | 0¦
Preliminary civil road design saved
|  | Soil/ Geotech ordered | Soil/ Geotech completed | 14¦
Soil/ Geotech completed
|  | Preliminary footing construction report ordered | Preliminary footing construction report complete | 21¦
|  | Preliminary footing construction report complete | All engineering reports reviewed | 0¦
|  | Wastewater septic Report ordered | Wastewater septic Report complete | 14¦
Wastewater septic Report complete
|  | All engineering and reports reviewed | All engineering reports issues rectified | 3¦
|  | All engineering and reports issues rectified | All engineering complete | 0¦
|  | All engineering complete | Order final development drawings | 0¦
|  | Land division plans ordered | Land division plans reviewed | 10¦
|  | Land division plans reviewed | Land division plans complete | 4¦
Land division plans complete
|  | Order final development drawings | Final development drawings complete | 1¦
|  | Final development drawings complete | Final development drawings approved ¦ Draft scheme description ordered (6 community dwellings or above only) ¦ Plan sent to Builders for 25% design cost estimates ¦ Building & Land div Plans submitted to council | 0¦0¦0¦1
|  | Final development drawings approved | Final development drawings saved | 0¦
Final development drawings saved
|  | Draft scheme description ordered (6 community dwellings or above only) | Draft scheme description complete | 7¦
|  | Draft scheme description complete | Draft scheme description saved | 0¦
Draft scheme description saved
|  | Plans sent to Builders for 25% design cost estimates | Construction 25% cost estimate complete | 7¦
|  | Construction 25% cost estimate complete | Construction 25% cost estimate saved ¦ Project program updated ¦ Preliminary costing complete ¦ Special conditions entered | 0¦0¦0¦0
Construction 25% cost estimate saved
Project program updated
Preliminary costing complete
Purchase & Finance
Responsible | Team | Task | Triggering task | days
|  | Signed purchase contract sent to Accounts | Deposit paid ¦ Special conditions entered | 5¦0
|  | Special conditions entered | Contract special conditions satisfied | 14¦
Deposit paid
|  | Contract special conditions satisfied | Purchase contract unconditional | 0¦
|  | Purchase contract unconditional | Settlement date scheduled ¦ Company set up | 0¦0¦
|  | Company set up | Bank account set up | 3¦
|  | Bank account set up | Loan applied - if required ¦ Job code and spreadsheet created in system | 3¦0
|  | Loan applied - if required | Send job feasibility spreadsheet to lender ¦ Valuation requested | 0¦0
|  | Settlement date scheduled | Settlement date confirmed with conveyancer | 2¦¦
|  | Settlement date confirmed with conveyancer | Funds available for purchase settlement confirmed ¦ Settlement statement reviewed and approved | 3¦0
|  | Funds available for purchase settlement confirmed | Purchase settlement funds sent to bank account ¦ Investors and sharesplits recorded | 1¦0
Job code and spreadsheet created in system
Purchase settlement funds sent to bank account
|  | Settlement statement reviewed and approved | Land Settlement | 0¦
Send job feasibility spreadsheet to lender
|  | Valuation requested | Valuation fee paid | 5¦
|  | Valuation fee paid | Valuation received | 14¦
|  | Valuation received | Land loan term sheet / pre-approval received | 7¦
|  | Land loan term sheet / pre-approval recieved | Loan conditions received | 2¦
Property insurance post land settlement - if required
|  | Building and PL insurance ordered | Building and PL insurance received | 0¦
|  | Building and PL insurance recieved | Building and PL insurance saved | 0¦
Building and PL insurance saved
|  | Land Loan conditions recieved | Land Loan conditions satisfied | 0¦
|  | Land Loan conditions satisifed | Land Loan unconditional | 3¦
|  | Land Loan unconditional | Land Loan docs signed | 0¦
|  | Land Loan docs signed | Loan Settlement | 1¦
|  | Loan Settlement | Loan amount and fees entered into job spreadsheet | 0¦
Loan amount and fees entered into job spreadsheet
|  | Land settlement | Property insurance post land settlement - if required | 0¦
|  | Investors and sharesplits recorded | Share certificate and receipt sent to investors | 0¦
Share certificate and receipt sent to investors
Council Approval
Responsible | Team | Task | Triggering task | days
|  | Building and Land div Plans submitted to council | Update Marketing on submission to council ¦ Verification RFI received ¦ Order front boundary pegging for SAWater | 0¦10¦0
|  | Order front boundary pegging for SAWater | Front boundary pegging for SAWater complete | 14¦
|  | Front boundary pegging for SAWater complete | Check new water meter location ¦ Boundary plans sent to SAWater for investigation | 0¦0
Check new water meter location
|  | Boundary plans sent to SAWater for investigation | SA water investigation complete | 21¦
Update Marketing on Submission to council
|  | Verification RFI recieved | Verification RFI items recorded below | 0¦
|  | Verification RFI items recorded below | All outstanding verification RFI docs sent to council | 5¦
|  | All outstanding verification RFI docs sent to council | Plans verified | 5¦
|  | Plans verified by council | Council approval fees paid | 1¦
|  | Council approval fees paid | Application RFI received | 21¦
|  | Application RFI recieved | Application RFI items recorded below | 0¦
|  | Application RFI items recorded below | All outstanding approval RFI docs sent to council | 5¦
|  | All outstanding approval RFI docs sent to council | Building Plans approved ¦ Land division approved | 7¦7
|  | Building Plans Approved | Building plans DNF conditions satisfied ¦ Working drawings commenced ¦ | 0¦0
Building plans DNF conditions satisfied
|  | Land division approved | Land division DNF conditions satisfied ¦ Marketing update - Plans Approved ¦ Final plans uploaded to SAPPA portal by surveyor ¦ SAPN connection ordered ¦ NBN connection ordered ¦ APA connection ordered ¦ Hydraulics design ordered (Sewer, Water, Gas) ¦ Telecomunications design ordered (NBN, Telstra) ¦ Electrical design ordered ¦ Road civil engineering ordered - if required | 0¦0¦3¦0¦0¦0¦0¦0¦0¦0
Land division DNF conditions satisfied
Marketing update - Plans Approved
Working drawings/ Selections
Responsible | Team | Task | Triggering task | days
|  | Working drawings commenced | Working drawings complete | 3¦
|  | Working drawings complete | Working drawings saved ¦ Working drawings signed off by management ¦ Final Landscaping plan ordered ¦ Selection schedule ordered ¦ Project feasibility updated ¦ Framing ordered ¦ Energy rating ordered ¦ Footings construction ordered ¦ CITB ordered | 0¦1¦1¦1¦1¦0¦0¦0¦0
Working drawings saved
Working drawings signed off by managment
|  | Final Landscaping plan ordered | Final Landscaping plan completed | 7¦
|  | Final Landscaping plan completed | Final Landscaping plan saved | 0¦
Landscaping plan saved
|  | Selection schedule ordered | Selection schedule complete | 2¦
Selection schedule complete
|  | Project feaisbility updated | Project feasibility saved to dropbox | 0¦
Project feaisbility saved to dropbox
Surveying
Responsible | Team | Task | Triggering task | days
|  | Final plans uploaded to SAPPA portal by surveyor | Request update from Surveyor on council clearance | 7¦
|  | Request update from Surveyor on council clearance | Council issues Final clearances complete | 7¦
|  | SA water investigation complete | SAWater connection sewer & water fees received ¦ SAWater connection sewer & water fees paid | 0¦0 | Added
SAWater connection sewer & water fees received
SAWater connection sewer & water fees paid
|  | Council issues Final clearances complete | Pay openspace | 0¦
|  | Pay openspace | Follow up surveyor for Land Division Certificate | 0¦
|  | Follow up surveyor for Land Division Certificate | Land Division Certificate received and saved from surveyor | 2¦
|  | Land Division Cetificate received and saved from surveyor | Surveyor Lodges final plans to LTO ¦ Final scheme description ordered (6 community titles) ¦ Confirm conveyancer has received Land Division Certificate | 0¦0¦0
|  | Surveyor Lodges final plans to LTO | LTO Approval on final plans | 7¦
|  | LTO Approval on final plans | Confirm surveyor has sent LTO plans to conveyancer | 0¦
|  | Confirm surveyor has sent LTO approved plans to conveyancer | Confirm conveyancer has lodged final Land Division plans to LTO | 1¦
|  | Confirm conveyancer has received Land Division Certificate | Confirm Conveyancer has requested bank discharges | 1¦
Conveyancing
Responsible | Team | Task | Triggering task | days
|  | Confirm Conveyancer has requested bank discharges | Bank discharge consent received | 5¦
Bank discharge consent recieved
|  | Final scheme description ordered (6 community titles) | Final scheme description completed (6 community titles) | 2¦
|  | Final scheme description completed (6 community titles) | Final scheme description saved (6 community titles) ¦ Final scheme description sent to surveyor | 0¦0
Final scheme description saved (6 community titles)
Final scheme description sent to surveyor
|  | Confirm conveyancer has lodged final Land Division plans to LTO | Titles issued | 3¦
|  | Titles issued | Titles saved | 0¦
|  | Titles saved | Title numbers issued to file | 0¦
Title numbers issued to file
Sales
Responsible | Team | Task | Triggering task | days
Sales agent confirmed
Agency signed
Sales and marketing material ordered
Sales and marketing material complete
Sales and marketing material saved
Land contracts and F1 ordered
Land contracts and F1 completed
Land contracts and F1 saved
Sales advertised
Engineering
Responsible | Team | Task | Triggering task | days
|  | Framing ordered | Framing complete | 28¦
|  | Framing complete | Framing reports saved ¦ All Engineering plans reviewed | 0¦0
Framing reports saved
|  | Footing construction ordered | Footing construction report complete | 14¦
|  | Footing construction report complete | Footing construction report saved | 0¦
Footing construction report saved
|  | Energy rating ordered | Energy rating complete | 14¦
|  | Energy rating complete | Energy rating saved | 0¦
Energy rating saved
|  | CITB ordered | CITB invoice received and sent to accounts | 0¦
|  | CITB invoice received and sent to accounts | CITB paid ¦ CITB receipt saved | 0¦0
CITB paid
CITB receipt saved
|  | Hydraulics design ordered (Sewer, water, gas) | Hydraulics design completed (Sewer, water, gas) | 14¦
|  | Telecommunications design ordered (NBN, Telstra) | Telecommunications design completed (NBN, Telstra) | 14¦
|  | Electrical design ordered | Electrical design completed | 14¦
|  | Hydraulics design completed (Sewer, water, gas) | Hydraulics design saved (Sewer, water, gas) | 0¦
|  | Telecommunications design completed (NBN, Telstra) | Telecommunications design saved (NBN, Telstra) | 0¦
|  | Electrical design completed | Electrical design saved | 0¦
Hydraulics design saved (Sewer, water, gas)
Telecommunications design saved (NBN, Telstra)
Electrical design saved
|  | SAPN new conncetion ordered | SAPN new connection fee received | 14¦
|  | SAPN new connection fee received | SAPN new connection fee paid | 7¦
SAPN new connection fee paid
|  | NBN new connection ordered | NBN new connection fee received | 14¦
|  | NBN new connection fee received | NBN new connection fee paid | 7¦
NBN new connection fee paid
|  | APA new connection ordered | APA new connection fee received | 14¦
|  | APA new conncetion fee received | APA new connection fee paid | 7¦
APA new conncetion fee paid
|  | Road civil engineering ordered - If required | Road civil engineering completed | 7¦
|  | Road civil engineering competed | Road civil engineering saved | 0¦
Road civil engineering saved
|  | All Engineering plans reviewed | All Engineering plans confirmed | 0¦
|  | All Engineering plans confirmed | All Engineering & WD plans checked | 1¦
Structural ordered - if required
Structural reports complete
Structural reports saved
|  | All Engineering & WD plans checked | All Engineering & WD plans updated (if reqd) | 0¦
|  | All Engineering & WD plans updated (if reqd) | All OLD Engineering & WD plans moved to superceded | 0¦
|  | All OLD Engineering & WD plans moved to superceded | All final engineering and working drawings sent to estimator | 0¦
|  | All final engineering and working drawings sent to estimator | Estimator confirms latest plan rev's ¦ Building contract ordered | 0¦0
Estimating
Responsible | Team | Task | Triggering task | days
|  | Estimator confirms latest plan rev's | Estimator sends 100% plans for quoting | 0¦
|  | Estimator sends 100% plans for quoting | All 100% plan quotes quotes received | 2¦
|  | All 100% plan quotes quotes received | Final development feasbility complete | 1¦
Final development feasbility complete
|  | Demolition quote requested | Demolition quote received | 1¦
Demolition quote received
|  | Demolition ordered | Update marketing on Demolition | 0¦
Update marketing on Demolition
Demolition started
Demolition complete
Demolition site checked
Demolition site photos saved
|  | Building contract ordered | Building contract conditions approved | 5¦
Bounary pegging plan ordered
Boundary pegging plan complete
Boundary pegging plan saved
|  | Building contract conditions approved | Building conctract executed | 2¦
|  | Building conctract executed | Building conctract saved | 0¦
Building conctract saved
Construction finance |  |  |  |  | Talk to Fiona
Responsible | Team | Task | Triggering task | days
Valutation ordered
Term sheet received
Term sheet reviewed
Finance amounts confirmed and recorded
All finance approval items submitted to lender
Construction finance unconditionall approved
HOW & PL Insurances ordered
HOW & PL Insurances complete
HOW & PL Insurances saved
Construction Loan docs recieved
Construction Loan docs reviewed
Construction Loan docs signed
Construction Loan docs sent to lender
Commencment letter received
Loan amounts and constibutions recorded
BRC/ DA
Responsible | Team | Task | Triggering task | days
|  | Draft construction drawings ordered | Draft construction drawings complete | 1¦
|  | Draft construction drawings complete | Draft construction drawings signed off | 0¦
|  | Draft construction drawings signed off | BRC submitted | 0¦
|  | Final construction drawings ordered | Final construction drawings complete
|  | Final construction drawings complete | Final construction drawings signed off ¦ Signed final construction drawings saved | 0¦0
Final construction drawings signed off
|  | Signed final construction drawings saved | Final build pack prepared with latest revisions | 0¦
|  | Final build pack prepared with latest revisions | Preconstruction team Pre-site meeting complete | 2¦
|  | Preconstruction team Pre-site meeting complete | Check & update latest rev drawings | 2¦
|  | Check & update latest rev drawings | Move all old rev plans into superceded files ¦ Final build pack sent to construction team | 0¦0
Move all old rev plans into superceded files
|  | Final build pack sent to construction team | Fencing notices for boundary property owners sent | 0¦
|  | BRC submitted | BRC received | 14¦
|  | BRC Received | DA received | 7¦
|  | DA received | Building and PL insurance ordered ¦ Final construction drawings ordered ¦ DA conditions reviewed and any issues rectified ¦ Project Program updated | 0¦0¦1¦1
DA conditions reviewed and any issues rectified
Project Program updated
Site works
Responsible | Team | Task | Triggering task | days
Fencing notices for boundary property owners sent
Construction site meeting complete
Site cut/ fill started
Site cut/ fill complete
Boundary retaining started
Boundary retaining completed
Site pads completed
Slab
|  | Slab started | Slab completed | 7¦
|  | Slab completed | Marketing update - Slab poured ¦ Invoice recieved ¦ Project engineer confirms slab check | 1¦0¦0
Project engineer confirms slab check
Marketing update - Slab poured
|  | Invoice recieved | Inspection complete ¦ Invoice checked | 0¦0
Inspection complete
|  | Invoice checked | Invoice paid | 0¦
Invoice paid
Frames
Frames started
Frames completed
Marketing update - Frames complete
Invoice recieved
Inspection complete
Invoice checked
Invoice paid
External Walls/ Roof
External walls started
External walls completed
Invoice recieved
Inspection complete
Invoice checked
Invoice paid
Internal Walls
Internal walls started
Internal walls completed
Invoice recieved
Inspection complete
Invoice checked
Invoice paid
Second Fix
Second Fix started
|  | Second Fix completed | PC started ¦ | 0
Invoice recieved
Inspection complete
Invoice checked
Invoice paid
Practical Completion
Dani |  | PC started | Walk through inspection booked with Builder ¦ | 0¦
Dani |  | Walk through inspection booked with Builder | Walk through complete ¦ Building inspection report complete ¦ Statement of compliance signed off by builder for all dwellings | 0¦0¦0
Sean |  | Walk through complete
Sean |  | Building inspection report complete | Defects noted ¦ | 0¦
Sean |  | Defects noted | Defects recitified by builder ¦ PC Complete | 0¦0
Sean |  | Defects recitified by builder | Final Walk through report sent to purchasers | 0¦
Dani |  | Final Walk through report sent to purchasers
Dani |  | PC Complete | Invoice recieved | 0¦
Kerri |  | Invoice recieved | Invoice checked | 0¦
Kerri |  | Invoice checked | Invoice paid | 0¦
Kerri |  | Invoice paid
Handover
Statement of compliance signed off by builder for all dwellings
Statement of compliance sent to purchasers
Images for defects libility period saved
Purchaser signs defects liability form
Handover complete
3 Month defect liability period commeced
3 Month defect liability period contact purchaser
3 Month defect liability period issues recoded
Defects rectified
Purchaser signs off defects rectified form
Signed defect rectification form saved
Project complete
All allotments settled
Final P&L complete
All itemized cost reviewed by managment
Capital distributed
Profit distributed
All BAS and Financial record updated
Project company deregistered