## NV Infill B&S
Residential multi-dwelling pre constructoin workflow
Preliminary planning
Responsible | Team | Task | Triggering task | days | NOTE
Baz | OM | Project team pre-planning meeting completed | Outer boundary & detailed survey Ordered ¦ Project program completed ¦ Book council meeting to discuss proposed plan ¦ Project Marketing strategy ordered ¦ Demolition Required | 0¦0¦0¦0¦0
Baz | OM | Project program completed | New electricity meter service connected ¦ New gas meter service connected | 0¦0
Mary | OA | Outer boundary & detailed survey Ordered | Outer boundary & detailed survey complete | 21¦
Mary | OA | Outer boundary & detailed survey complete
Sean | Design | Book council meeting to discuss proposed plan | Council meeting complete | 7¦
Sean | Design | Council meeting complete | Final concept plans ordered | 0¦
Dianna | Marketing | Project Marketing strategy ordered | Project Marketing Strategy complete | 1¦
Dianna | Marketing | Project Marketing Strategy complete
Baz | OM | Demolition Required | Demolition quote requested | 0¦
Sean | Design | Final concept plans ordered | Final concept plans completed | 3¦
Sean | Design | Final concept plans completed | Planning drawings ordered | 0¦
Rochelle | Reception | New electricity meter service connected | Elec abolishment ordered | 14¦
Rochelle | Reception | New gas meter service connected | Gas abolishment ordered | 14¦
Rochelle | Reception | Elec abolishment ordered | Elec services abolishment approved | 5¦
Rochelle | Reception | Gas abolishment ordered | Gas services abolishment approved | 5¦
Rochelle | Reception | Gas services abolishment approved | Gas abolished confirmed | 5¦
Rochelle | Reception | Elec services abolishment approved | Confirm SAPN electricity abolishment request sent to SAPN by service provider | 0¦
Rochelle | Reception | Confirm SAPN electricity abolishment request sent to SAPN by electricity provider | Electricity abolishment booked with SAPN | 5¦
Rochelle | Reception | Electricity abolishment booked with SAPN | Electricity abolished | 14¦
Rochelle | Reception | Electricity abolished | Electricity abolishment site check | 2¦
Rochelle | Reception | Electricity abolishment site check
Rochelle | Reception | Gas abolished confirmed | Gas abolished site check | 2¦
Rochelle | Reception | Gas abolished site check
Sean | Design | Planning drawings ordered | Planning drawings complete ¦ EPA report ordered ¦ Native veg report ordered ¦ Arborist report ordered ¦ Site & Drainage stormwater plan ordered ¦ Land division plans ordered ¦ Hydraulics services ordered (Sewer, water, gas) ¦ Telecomunications ordered (NBN, Telstra ¦ Electrical services ordered ¦ Preliminary footing construction report ordered ¦ Preliminary civil road design ordered ¦ Soil/ Geotech ordered ¦ Wastewater septic Report ordered ¦ Landscaping concept plan ordered | 3¦0¦0¦0¦0¦0¦0¦0¦0¦0¦0¦0¦0¦0
Sean | Design | Planning drawings complete
Sean | Design | Landscaping concept plan ordered | Landscaping concept plan complete | 14¦
Sean | Design | Landscaping concept plan complete
Sean | Design | EPA report ordered | EPA report complete | 21¦
Sean | Design | EPA report complete
Sean | Design | Native veg report ordered | Native veg report complete | 28¦
Sean | Design | Native veg report complete
Sean | Design | Arborist report ordered | Arborist report complete | 21¦
Sean | Design | Arborist report complete
Baz | OM | Hydraulics services ordered (Sewer, water, gas)
Baz | OM | Telecommunications ordered (NBN, Telstra)
Baz | OM | Electrical services ordered
Baz | OM | Site & Drainage stormwater plan ordered | Site & Drainage stormwater plan Complete | 14¦
Baz | OM | Site & Drainage stormwater plan Complete
Baz | OM | Preliminary civil road design ordered | Preliminary civil road design completed | 7¦
Baz | OM | Preliminary civil road design completed | Preliminary civil design saved | 0¦
Baz | OM | Preliminary civil road design saved
Baz | OM | Soil/ Geotech ordered | Soil/ Geotech completed | 14¦
Baz | OM | Soil/ Geotech completed
Sean | Design | Preliminary footing construction report ordered | Preliminary footing construction report complete | 21¦
Sean | Design | Preliminary footing construction report complete | All engineering reports reviewed | 0¦
Sean | Design | Wastewater septic Report ordered | Wastewater septic Report complete | 14¦
Sean | Design | Wastewater septic Report complete
Sean | Design | All engineering and reports reviewed | All engineering reports issues rectified | 3¦
Sean | Design | All engineering and reports issues rectified | All engineering complete | 0¦
Sean | Design | All engineering complete | Order final development drawings | 0¦
Sean | Design | Land division plans ordered | Land division plans reviewed | 10¦
Sean | Design | Land division plans reviewed | Land division plans complete | 4¦
Sean | Design | Land division plans complete
Sean | Design | Order final development drawings | Final development drawings complete | 1¦
Sean | Design | Final development drawings complete | Final development drawings approved ¦ Draft scheme description ordered (6 community dwellings or above only) ¦ Plan sent to Builders for 25% design cost estimates ¦ Building & Land div Plans submitted to council | 0¦0¦0¦1
Sean | Design | Final development drawings approved | Final development drawings saved | 0¦
Sean | Design | Final development drawings saved
Baz | OM | Draft scheme description ordered (6 community dwellings or above only) | Draft scheme description complete | 7¦
Baz | OM | Draft scheme description complete | Draft scheme description saved | 0¦
Baz | OM | Draft scheme description saved
Baz | OM | Plans sent to Builders for 25% design cost estimates | Construction 25% cost estimate complete | 7¦
Baz | OM | Construction 25% cost estimate complete | Construction 25% cost estimate saved ¦ Project program updated ¦ Preliminary costing complete ¦ Special conditions entered | 0¦0¦0¦0
Baz | OM | Construction 25% cost estimate saved
Baz | OM | Project program updated
Baz | OM | Preliminary costing complete
Purchase & Finance
Responsible | Team | Task | Triggering task | days
Fiona | Finance | Signed purchase contract sent to Accounts | Deposit paid ¦ Special conditions entered | 5¦0
Fiona | Finance | Special conditions entered | Contract special conditions satisfied | 14¦
Fiona | Finance | Deposit paid
Fiona | Finance | Contract special conditions satisfied | Purchase contract unconditional | 0¦
Fiona | Finance | Purchase contract unconditional | Settlement date scheduled ¦ Company set up | 0¦0¦
Fiona | Finance | Company set up | Bank account set up | 3¦
Fiona | Finance | Bank account set up | Loan applied - if required ¦ Job code and spreadsheet created in system | 3¦0
Fiona | Finance | Loan applied - if required | Send job feasibility spreadsheet to lender ¦ Valuation requested | 0¦0
Fiona | Finance | Settlement date scheduled | Settlement date confirmed with conveyancer | 2¦¦
Fiona | Finance | Settlement date confirmed with conveyancer | Funds available for purchase settlement confirmed ¦ Settlement statement reviewed and approved | 3¦0
Fiona | Finance | Funds available for purchase settlement confirmed | Purchase settlement funds sent to bank account ¦ Investors and sharesplits recorded | 1¦0
Fiona | Finance | Job code and spreadsheet created in system
Fiona | Finance | Purchase settlement funds sent to bank account
Fiona | Finance | Settlement statement reviewed and approved | Land Settlement | 0¦
Fiona | Finance | Send job feasibility spreadsheet to lender
Fiona | Finance | Valuation requested | Valuation fee paid | 5¦
Fiona | Finance | Valuation fee paid | Valuation received | 14¦
Fiona | Finance | Valuation received | Land loan term sheet / pre-approval received | 7¦
Fiona | Finance | Land loan term sheet / pre-approval recieved | Loan conditions received | 2¦
Fiona | Finance | Property insurance post land settlement - if required
Fiona | Finance | Building and PL insurance ordered | Building and PL insurance received | 0¦
Fiona | Finance | Building and PL insurance recieved | Building and PL insurance saved | 0¦
Fiona | Finance | Building and PL insurance saved
Fiona | Finance | Land Loan conditions recieved | Land Loan conditions satisfied | 0¦
Fiona | Finance | Land Loan conditions satisifed | Land Loan unconditional | 3¦
Fiona | Finance | Land Loan unconditional | Land Loan docs signed | 0¦
Fiona | Finance | Land Loan docs signed | Loan Settlement | 1¦
Fiona | Finance | Loan Settlement | Loan amount and fees entered into job spreadsheet | 0¦
Fiona | Finance | Loan amount and fees entered into job spreadsheet
Fiona | Finance | Land settlement | Property insurance post land settlement - if required | 0¦
Fiona | Finance | Investors and sharesplits recorded | Share certificate and receipt sent to investors | 0¦
Fiona | Finance | Share certificate and receipt sent to investors
Council Approval
Responsible | Team | Task | Triggering task | days
Sean | Design | Building and Land div Plans submitted to council | Update Marketing on submission to council ¦ Verification RFI received ¦ Order front boundary pegging for SAWater ¦ Construction valuation ordered | 0¦10¦0¦0
Sean | Design | Order front boundary pegging for SAWater | Front boundary pegging for SAWater complete | 14¦
Sean | Design | Front boundary pegging for SAWater complete | Check new water meter location ¦ Boundary plans sent to SAWater for investigation | 0¦0
Sean | Design | Check new water meter location
Sean | Design | Boundary plans sent to SAWater for investigation | SA water investigation complete | 21¦
Sean | Design | Update Marketing on Submission to council
Sean | Design | Verification RFI recieved | Verification RFI items recorded below | 0¦
Sean | Design | Verification RFI items recorded below | All outstanding verification RFI docs sent to council | 5¦
Sean | Design | All outstanding verification RFI docs sent to council | Plans verified | 5¦
Sean | Design | Plans verified by council | Council approval fees paid | 1¦
Sean | Design | Council approval fees paid | Application RFI received | 21¦
Sean | Design | Application RFI recieved | Application RFI items recorded below | 0¦
Sean | Design | Application RFI items recorded below | All outstanding approval RFI docs sent to council | 5¦
Sean | Design | All outstanding approval RFI docs sent to council | Building Plans approved ¦ Land division approved | 7¦7
Sean | Design | Building Plans Approved | Building plans DNF conditions satisfied ¦ Working drawings commenced ¦ Land contracts and F1 ordered ¦ | 0¦0¦0¦0
Sean | Design | Building plans DNF conditions satisfied
Sean | Design | Land division approved | Land division DNF conditions satisfied ¦ Marketing update - Plans Approved ¦ Final plans uploaded to SAPPA portal by surveyor ¦ SAPN connection ordered ¦ NBN connection ordered ¦ APA connection ordered ¦ Hydraulics design ordered (Sewer, Water, Gas) ¦ Telecomunications design ordered (NBN, Telstra) ¦ Electrical design ordered ¦ Road civil engineering ordered - if required | 0¦0¦3¦0¦0¦0¦0¦0¦0¦0
Sean | Design | Land division DNF conditions satisfied
Sean | Design | Marketing update - Plans Approved
Working drawings/ Selections
Responsible | Team | Task | Triggering task | days
Sean | Design | Working drawings commenced | Working drawings complete | 3¦
Sean | Design | Working drawings complete | Working drawings saved ¦ Working drawings signed off by management ¦ Final Landscaping plan ordered ¦ Selection schedule ordered ¦ Project feasibility updated ¦ Framing ordered ¦ Energy rating ordered ¦ Footings construction ordered ¦ CITB ordered ¦ Sales & marketing material ordered ¦ | 0¦1¦1¦1¦1¦0¦0¦0¦0¦0
Sean | Design | Working drawings saved
Sean | Design | Working drawings signed off by managment
Sean | Design | Final Landscaping plan ordered | Final Landscaping plan completed | 7¦
Sean | Design | Final Landscaping plan completed | Final Landscaping plan saved | 0¦
Sean | Design | Landscaping plan saved
Baz | OM | Selection schedule ordered | Selection schedule complete | 2¦
Baz | OM | Selection schedule complete
Baz | OM | Project feaisbility updated | Project feasibility saved to dropbox | 0¦
Baz | OM | Project feaisbility saved to dropbox
Surveying
Responsible | Team | Task | Triggering task | days
Baz | OM | Final plans uploaded to SAPPA portal by surveyor | Request update from Surveyor on council clearance | 7¦
Baz | OM | Request update from Surveyor on council clearance | Council issues Final clearances complete | 7¦
Baz | OM | SA water investigation complete | SAWater connection sewer & water fees received ¦ SAWater connection sewer & water fees paid | 0¦0 | Added
Baz | OM | SAWater connection sewer & water fees received
Baz | OM | SAWater connection sewer & water fees paid
Baz | OM | Council issues Final clearances complete | Pay openspace | 0¦
Baz | OM | Pay openspace | Follow up surveyor for Land Division Certificate | 0¦
Baz | OM | Follow up surveyor for Land Division Certificate | Land Division Certificate received and saved from surveyor | 2¦
Baz | OM | Land Division Cetificate received and saved from surveyor | Surveyor Lodges final plans to LTO ¦ Final scheme description ordered (6 community titles) ¦ Confirm conveyancer has received Land Division Certificate | 0¦0¦0
Baz | OM | Surveyor Lodges final plans to LTO | LTO Approval on final plans | 7¦
Baz | OM | LTO Approval on final plans | Confirm surveyor has sent LTO plans to conveyancer | 0¦
Baz | OM | Confirm surveyor has sent LTO approved plans to conveyancer | Confirm conveyancer has lodged final Land Division plans to LTO | 1¦
Baz | OM | Confirm conveyancer has received Land Division Certificate | Confirm Conveyancer has requested bank discharges | 1¦
Conveyancing
Responsible | Team | Task | Triggering task | days
Baz | OM | Confirm Conveyancer has requested bank discharges | Bank discharge consent received | 5¦
Baz | OM | Bank discharge consent recieved | Sales agent confirmed | 0¦
Baz | OM | Final scheme description ordered (6 community titles) | Final scheme description completed (6 community titles) | 2¦
Baz | OM | Final scheme description completed (6 community titles) | Final scheme description saved (6 community titles) ¦ Final scheme description sent to surveyor | 0¦0
Baz | OM | Final scheme description saved (6 community titles)
Baz | OM | Final scheme description sent to surveyor
Baz | OM | Confirm conveyancer has lodged final Land Division plans to LTO | Titles issued | 3¦
Baz | OM | Titles issued | Titles saved ¦ All allotments settled | 0¦21
Mary | OA | Titles saved | Title numbers issued to file | 0¦
Mary | OA | Title numbers issued to file
Sales
Responsible | Team | Task | Triggering task | days
Baz | OM | Sales agent confirmed | Agency signed | 1¦
Baz | OM | Agency signed
Diana | Marketing | Sales and marketing material ordered | Sales and marketing material complete | 14¦
Diana | Marketing | Sales and marketing material complete | Sales and marketing material saved ¦ Sales advertised | 0¦0
Diana | Marketing | Sales and marketing material saved
Rochelle | Reception | Land contracts and F1 ordered | Land F1 complete ¦ Land contract completed | 14¦7
Rochelle | Reception | Land F1 completed | Land contracts and F1 saved | 0¦
Rochelle | Reception | Land contract completed
Rochelle | Reception | Land contracts and F1 saved
Diana | Marketing | Sales advertised
Engineering
Responsible | Team | Task | Triggering task | days
Mary | OA | Framing ordered | Framing complete | 28¦
Mary | OA | Framing complete | Framing reports saved ¦ All Engineering plans reviewed | 0¦0
Mary | OA | Framing reports saved
Mary | OA | Footing construction ordered | Footing construction report complete | 14¦
Mary | OA | Footing construction report complete | Footing construction report saved | 0¦
Mary | OA | Footing construction report saved
Mary | OA | Energy rating ordered | Energy rating complete | 14¦
Mary | OA | Energy rating complete | Energy rating saved | 0¦
Mary | OA | Energy rating saved
Mary | OA | CITB ordered | CITB invoice received and sent to accounts | 0¦
Mary | OA | CITB invoice received and sent to accounts | CITB paid ¦ CITB receipt saved | 0¦0
Mary | OA | CITB paid
Mary | OA | CITB receipt saved
Baz | OM | Hydraulics design ordered (Sewer, water, gas) | Hydraulics design completed (Sewer, water, gas) | 14¦
Baz | OM | Telecommunications design ordered (NBN, Telstra) | Telecommunications design completed (NBN, Telstra) | 14¦
Baz | OM | Electrical design ordered | Electrical design completed | 14¦
Baz | OM | Hydraulics design completed (Sewer, water, gas) | Hydraulics design saved (Sewer, water, gas) | 0¦
Baz | OM | Telecommunications design completed (NBN, Telstra) | Telecommunications design saved (NBN, Telstra) | 0¦
Baz | OM | Electrical design completed | Electrical design saved | 0¦
Baz | OM | Hydraulics design saved (Sewer, water, gas)
Baz | OM | Telecommunications design saved (NBN, Telstra)
Baz | OM | Electrical design saved
Baz | OM | SAPN new conncetion ordered | SAPN new connection fee received | 14¦
Baz | OM | SAPN new connection fee received | SAPN new connection fee paid | 7¦
Baz | OM | SAPN new connection fee paid
Baz | OM | NBN new connection ordered | NBN new connection fee received | 14¦
Baz | OM | NBN new connection fee received | NBN new connection fee paid | 7¦
Baz | OM | NBN new connection fee paid
Baz | OM | APA new connection ordered | APA new connection fee received | 14¦
Baz | OM | APA new conncetion fee received | APA new connection fee paid | 7¦
Baz | OM | APA new conncetion fee paid
Baz | OM | Road civil engineering ordered - If required | Road civil engineering completed | 7¦
Baz | OM | Road civil engineering competed | Road civil engineering saved | 0¦
Baz | OM | Road civil engineering saved
Baz | OM | All Engineering plans reviewed | All Engineering plans confirmed | 0¦
Baz | OM | All Engineering plans confirmed | All Engineering & WD plans checked | 1¦
Sean | Design | Structural ordered - if required
Sean | Design | Structural reports complete
Sean | Design | Structural reports saved
Sean | Design | All Engineering & WD plans checked | All Engineering & WD plans updated (if reqd) | 0¦
Sean | Design | All Engineering & WD plans updated (if reqd) | All OLD Engineering & WD plans moved to superceded | 0¦
Sean | Design | All OLD Engineering & WD plans moved to superceded | All final engineering and working drawings sent to estimator | 0¦
Sean | Design | All final engineering and working drawings sent to estimator | Estimator confirms latest plan rev's ¦ Building contract ordered | 0¦0
Estimating
Responsible | Team | Task | Triggering task | days
Baz | OM | Estimator confirms latest plan rev's | Estimator sends 100% plans for quoting | 0¦
Baz | OM | Estimator sends 100% plans for quoting | All 100% plan quotes quotes received | 2¦
Baz | OM | All 100% plan quotes quotes received | Final development feasbility complete | 1¦
Baz | OM | Final development feasbility complete
Baz | OM | Demolition quote requested | Demolition quote received | 1¦
Baz | OM | Demolition quote received | Demolition removal plan ordered | 0¦
Baz | OM | Demolition removal plan ordered | Demolition removal plan completed | 1¦
Baz | OM | Demolition removal plan completed | Demolition removal plan sentto Demolition company | 0¦
Baz | OM | Demolition removal plan sent to Demolition company
Baz | OM | Demolition ordered | Update marketing on Demolition | 0¦
Baz | OM | Update marketing on Demolition
Baz | OM | Demolition started | Boundary pegging plan ordered ¦ Demolition complete | 0¦7
Baz | OM | Demolition complete | Demolition site checked | 1¦
Baz | OM | Demolition site checked | Demolition site photos saved | 0¦
Baz | OM | Demolition site photos saved
Baz | OM | Building contract ordered | Building contract conditions approved | 5¦
Baz | OM | Boundary pegging plan ordered | Boundary pegging plan complete | 14¦
Baz | OM | Boundary pegging plan complete | Boundary pegging plan saved | 0¦
Baz | OM | Boundary pegging plan saved
Baz | OM | Building contract conditions approved | Building contract executed | 2¦
Baz | OM | Building contract executed | Building contract saved | 0¦
Baz | OM | Building contract saved
Construction finance
Responsible | Team | Task | Triggering task | days
Fiona | Finance | Construction valuation ordered | Finance amounts confirmed and recorded ¦ Term sheet received ¦ Construction valuation complete | 7¦7¦7
Fiona | Finance | Construction valuation complete
Fiona | Finance | Term sheet received | Term sheet reviewed | 0¦
Fiona | Finance | Term sheet reviewed
Fiona | Finance | Finance amounts confirmed and recorded | All finance approval items submitted to lender ¦ HOW & PL insurances ordered | 0¦0
Fiona | Finance | All finance approval items submitted to lender | Construction finance unconditionall approved | 14¦
Fiona | Finance | Construction finance unconditionall approved | Construction Loan docs recieved | 7¦
Fiona | Finance | HOW & PL Insurances ordered | HOW & PL Insurances complete | 2¦
Fiona | Finance | HOW & PL Insurances complete | HOW & PL Insurances saved | 0¦
Fiona | Finance | HOW & PL Insurances saved
Fiona | Finance | Construction Loan docs recieved | Construction Loan docs reviewed | 0¦
Fiona | Finance | Construction Loan docs reviewed | Construction Loan docs signed | 0¦
Fiona | Finance | Construction Loan docs signed | Construction Loan docs sent to lender | 0¦
Fiona | Finance | Construction Loan docs sent to lender | Commencement letter received | 14¦
Fiona | Finance | Commencement letter received | Loan amounts and constibutions recorded | 0¦
Fiona | Finance | Loan amounts and constibutions recorded
BRC/ DA
Responsible | Team | Task | Triggering task | days
Sean | Design | Draft construction drawings ordered | Draft construction drawings complete | 1¦
Sean | Design | Draft construction drawings complete | Draft construction drawings signed off | 0¦
Sean | Design | Draft construction drawings signed off | BRC submitted | 0¦
Sean | Design | Final construction drawings ordered | Final construction drawings complete
Sean | Design | Final construction drawings complete | Final construction drawings signed off ¦ Signed final construction drawings saved | 0¦0
Sean | Design | Final construction drawings signed off
Sean | Design | Signed final construction drawings saved | Final build pack prepared with latest revisions | 0¦
Sean | Design | Final build pack prepared with latest revisions | Preconstruction team Pre-site meeting complete | 2¦
Sean | Design | Preconstruction team Pre-site meeting complete | Check & update latest rev drawings | 2¦
Sean | Design | Check & update latest rev drawings | Move all old rev plans into superceded files ¦ Final build pack sent to construction team | 0¦0
Sean | Design | Move all old rev plans into superceded files
Sean | Design | Final build pack sent to construction team | Fencing notices for boundary property owners sent | 0¦
Mary | OA | BRC submitted | BRC received | 14¦
Mary | OA | BRC Received | DA received | 7¦
Mary | OA | DA received | Building and PL insurance ordered ¦ Final construction drawings ordered ¦ DA conditions reviewed and any issues rectified ¦ Project Program updated | 0¦0¦1¦1
Mary | OA | DA conditions reviewed and any issues rectified
Baz | OM | Project Program updated
Site works
Responsible | Team | Task | Triggering task | days
Mary | OA | Fencing notices for boundary property owners sent | Construction site meeting complete | 3¦
Mary | OA | Construction site meeting complete | Site cut/ fill started | 2¦
Mary | OA | Site cut/ fill started | Site cut/ fill complete | 0¦
Mary | OA | Site cut/ fill complete | Boundary retaining started | 7¦
Mary | OA | Boundary retaining started | Boundary retaining completed | 4¦
Mary | OA | Boundary retaining completed
Slab
Mary | OA | Slab started | Slab completed | 7¦
Mary | OA | Slab completed | Marketing update - Slab poured ¦ Invoice recieved | 1¦0¦
Mary | OA | Marketing update - Slab poured
Fiona | Finance | Invoice recieved | Inspection complete ¦ Invoice checked | 0¦0
Fiona | Finance | Inspection complete
Fiona | Finance | Invoice checked | Invoice paid | 0¦
Fiona | Finance | Invoice paid | Frames started | 10¦
Frames
Mary | OA | Frames started | Frames completed | 10¦
Mary | OA | Frames completed | Marketing update - Frames complete ¦ Invoice recieved | 1¦0
Mary | OA | Marketing update - Frames complete
Fiona | Finance | Invoice recieved | Inspection complete ¦ Invoice checked | 0¦0
Fiona | Finance | Inspection complete
Fiona | Finance | Invoice checked | Invoice paid | 0¦
Fiona | Finance | Invoice paid | External walls started | 14¦
External Walls/ Roof
Mary | OA | External walls started | External Walls completed ¦ | 14¦
Mary | OA | External walls completed | Invoice recieved | 0¦
Fiona | Finance | Invoice recieved | Inspection complete ¦ Invoice checked | 0¦0
Fiona | Finance | Inspection complete
Fiona | Finance | Invoice checked | Invoice paid | 0¦
Fiona | Finance | Invoice paid | Internal walls started | 14¦
Internal Walls
Mary | OA | Internal walls started | Internal walls completed | 14¦
Mary | OA | Internal walls completed | Invoice recieved | 0¦
Fiona | Finance | Invoice recieved | Inspection complete ¦ Invoice checked | 0¦0
Fiona | Finance | Inspection complete
Fiona | Finance | Invoice checked | Invoice paid | 0¦
Fiona | Finance | Invoice paid | Second Fix started | 7¦
Second Fix
Mary | OA | Second Fix started | Second Fix completed | 28¦
Mary | OA | Second Fix completed | Invoice received | 0¦
Mary | OA | Invoice recieved | Inspection complete ¦ Invoice checked | 0¦0
Mary | OA | Inspection complete
Mary | OA | Invoice checked | Invoice paid | 0¦
Mary | OA | Invoice paid | PC started | 0¦
Practical Completion
Mary | OA | PC started | Walk through inspection booked with Builder ¦ | 0¦
Mary | OA | Walk through inspection booked with Builder | Walk through complete ¦ Building inspection report complete ¦ Statement of compliance signed off by builder for all dwellings | 0¦0¦0
Mary | OA | Walk through complete
Mary | OA | Building inspection report complete | Defects noted ¦ | 0¦
Mary | OA | Defects noted | Defects recitified by builder ¦ PC Complete | 0¦0
Mary | OA | Defects recitified by builder | Final Walk through report sent to purchasers | 0¦
Mary | OA | Final Walk through report sent to purchasers
Mary | OA | PC Complete | Invoice recieved | 0¦
Fiona | Finance | Invoice recieved | Invoice checked | 0¦
Fiona | Finance | Invoice checked | Invoice paid | 0¦
Fiona | Finance | Invoice paid
Handover
Mary | OA | Statement of compliance signed off by builder for all dwellings | Statement of compliance sent to purchasers | 0¦
Mary | OA | Statement of compliance sent to purchasers | Images for defects laibility period saved | 0¦
Mary | OA | Images for defects laibility period saved | Purchaser signs defects liability form | 0¦
Mary | OA | Purchaser signs defects liability form | Handover complete | 0¦
Mary | OA | Handover complete | 3 Month defect liability period commenced | 0¦
Mary | OA | 3 Month defect liability period commenced | 3 Month defect liability period contact purchaser | 90¦
Mary | OA | 3 Month defect liability period contact purchaser | 3 Month defect liability period issues recoded | 0¦
Mary | OA | 3 Month defect liability period issues recoded | Defects rectified | 30¦
Mary | OA | Defects rectified | Purchaser signs off defects rectified form | 0¦
Mary | OA | Purchaser signs off defects rectified form | Signed defect rectification form saved | 0¦
Mary | OA | Signed defect rectification form saved
Project complete
Fiona | Finance | All allotments settled | Final P&L complete | 0¦
Fiona | Finance | Final P&L complete | All itemized cost reviewed by managment | 0¦
Fiona | Finance | All itemized cost reviewed by managment | Capital distributed | 2¦
Fiona | Finance | Capital distributed | Profit distributed | 0¦
Fiona | Finance | Profit distributed | All BAS and Financial record updated | 0¦
Fiona | Finance | All BAS and Financial record updated | Project company deregistered | 0¦
Fiona | Finance | Project company deregistered